## SOP
STANDARD OPERATING PROCEDURE — Equipment Forecasting & Install Tracker
Last updated: July 30, 2026 · Questions: contact the service manager
Jump to a tab:
→ Dashboard
→ Projected Sales or Lease
→ Installs
→ Lists
→ Install Clock
WHAT EACH TAB DOES
SOP — this page. How to use the file.
Dashboard — live sales performance summary. All numbers update automatically; never type on this tab.
Projected Sales or Lease — the SALES TEAM works here. One row per high-value equipment deal.
Installs — the SERVICE TEAM works here. Tracks equipment through benching and installation.
Lists — the dropdown menus live here. Add new producers or options here and every tab updates automatically.
Install Clock — read-only watch list: who is at risk this week and what to prep next. Nothing is typed here.
SALES TEAM — ENTERING A DEAL (Projected Sales or Lease tab)
1. Start a new row: enter Customer Name, pick the Producer from the dropdown, and enter the Date of Deal.
2. Account Type: ONLY used for Avi or Richard accounts (they do not have access to this file). Pick "Avi Account" or "Richard Account" from the dropdown so we know who owns it. Leave blank for everyone else. This flag stays on this tab — it does not transfer to Installs.
3. Fill in Equipment and Deal Amount ($). A yellow Deal Amount cell means the amount is missing — the Dashboard cannot count the deal’s value until it’s entered.
4. Check Good to Order ✔ when the deal is approved to purchase, and Equipment Ordered ✔ once the order is placed. Enter the Equipment ETA when known.
5. Pick the Payment Terms from the dropdown and enter the Invoice # when issued.
DEAL COMPLETION — THE IMPORTANT COLUMN
✔ (checked) = the deal is FINALIZED. The row turns GREEN, the deal counts as Completed on the Dashboard, and the deal automatically appears in the Installs tab (see next section).
X = the deal FELL THROUGH. The row turns RED and the deal is excluded from every Dashboard figure except the "Fell Through" count. Leave the row in place — do not delete it.
Blank = deal is still active / in the pipeline.
AUTOMATIC TRANSFER TO THE INSTALLS TAB
When Deal Completion is checked ✔, the deal is copied into the "AUTO — NEW COMPLETED DEALS" section near the bottom of the Installs tab (starting at row 161) — but ONLY if that Customer Name is not already in the tracker above. Deals the service team is already tracking are never duplicated.
What transfers: Date (from Date of Deal) · Customer Name · Equipment · Account Rep (the producer’s full name converts to initials: Bill→BM, Lance→LO, Sean→SM, Shannon→SC, Lizbeth→LR, Amanda→AL, Jesus→JG) · Payment Status (from Payment Terms).
The transferred cells show in GREEN TEXT — they are live formulas. Do NOT type over them; they update on their own. If a name or date is wrong, fix it on the Projected Sales or Lease tab and it corrects itself here.
The service team fills in the normal columns by hand for those rows: Equipment Status, Install Date, Assigned Tech, Work Order, Requirements Ready?, and Notes. Install Complete ✔ fills itself when Status = Installed.
Because the check is on Customer Name, the sales tab and the install tab must spell an account the same way. If a completed deal does not appear in the AUTO section and is not already in the tracker, check for a spelling difference.
DASHBOARD — READING THE NUMBERS
KPI cards (top): Active Deals & Active Pipeline $ (deals still open) · Completed Deals & $ · Total Booked $ (active + completed) · Fell Through count.
BY PRODUCER: each producer’s deal count, Sales $ vs Lease $ (Lease = Payment Terms is "Lease"), completed figures, and Open $. "(No producer / not on list)" catches deals with a blank producer or a name not on the Lists tab — the TOTAL row always matches the KPI cards.
BY PAYMENT TERMS and DEAL PROGRESS: how the pipeline splits by terms, and how many deals (and $) have reached Good to Order → Equipment Ordered → Complete.
ADDING OR CHANGING NAMES AND DROPDOWNS (Lists tab)
New producer: type the name at the bottom of the "Producers" column (column Q). It instantly appears in the Producer dropdown and gets its own Dashboard row.
IMPORTANT: also add their initials to the mapping table in columns U–V ("Producer (map)" / "Initials") so completed deals transfer to Installs with the right Account Rep initials.
Payment terms, account types, statuses, reps, and technicians all live on this tab too — add to the bottom of the relevant column.
DO / DON’T
DO: use the dropdowns · fill Date of Deal and Deal Amount on every deal · mark X instead of deleting a dead deal.
DON’T: insert or delete COLUMNS on the Projected or Installs tabs (formulas point at fixed columns) · type in green formula cells · type on the Dashboard · delete, sort, or filter rows in the AUTO section of Installs (the filter buttons at the top of Installs only cover the manual rows 3–148). Do not convert the Installs sheet to an Excel Table — it conflicts with the AUTO section.
SERVICE TEAM — THE INSTALLS TAB
Enter one row per account. Type into the next EMPTY row — do not insert rows (an inserted row comes in without the Install Complete and Install Alert formulas, so it will never flag). Blank rows are already prepared down to row 170.
Equipment Status (dropdown): Ready · Not Ready · Installed. This drives the row color and the Install Clock.
Install Date: enter a REAL DATE (7/27/2026), not text like "week of 7/27". Text dates cannot be scheduled and get flagged "⚠ CHECK DATE".
Assigned Tech (dropdown): Josh, Oliver, Charles, Elias, Ryan, Bill, Lance, 3rd Party. Managed on the Lists tab, "Technicians" column A.
Requirements Ready? (dropdown): Ready / Not Ready — is the CUSTOMER ready for us to install (site, power, plumbing, sign-off)?
Install Complete ✔ and ⚠ Install Alert fill in on their own — do not type in them.
ROW COLORS — ONE RULE FOR EVERY ROW
RED = needs attention now (anything in the ⚠ Install Alert column). Beats every other color.
GREEN = Equipment Status is Installed — done.
AMBER = Equipment Status is Not Ready (and not urgent yet).
BLUE = Equipment Status is Ready — waiting on the install date.
Plain / faint stripe = no status picked yet.
Every row in the tracker, including the AUTO section, follows this exact order. If a row is not coloring, its Equipment Status cell is empty or was typed by hand instead of picked from the dropdown (watch for stray spaces).
THE INSTALL CLOCK (its own tab)
The Installs tab shows the counters across the top; the Install Clock tab shows the full detail. It reads the current calendar week (Monday–Sunday) plus the following week, and watches every account with an install date in that window.
⚠ EQUIP NOT READY — install is this week or next and Equipment Status is Not Ready. This is the main one to work.
⚠ PAST DUE - NOT READY — the install date has already passed and the equipment still is not ready.
⚠ CUSTOMER NOT READY — equipment is fine but Requirements Ready? is Not Ready and the install is this week or next.
⚠ CHECK DATE — Not Ready account whose Install Date is text, so it cannot be scheduled. Replace it with a real date.
Everything refreshes when the file is opened or recalculated (F9). The AT RISK list shows the first 10 and the PREP QUEUE the next 20; the note under each says how many more there are.
Installed accounts are never flagged.
INSTALL DATES — CALENDAR DATES ONLY
Date Received and Install Date now only accept a real calendar date. Typing "week of 8/3" is rejected with a message explaining why.
Fastest ways to enter one: type 8/3/26 · press Ctrl + ; for today · or copy a date cell and paste.
If you only know the week, enter the MONDAY of that week and put the detail in Notes. A week-only note cannot be scheduled or counted.
Existing "week of ..." entries were converted to the date named, and the original wording was added to that row’s Notes.
PREP QUEUE — WHAT TO GET READY NEXT
On the Install Clock tab, under the at-risk list. It lists every account NOT yet marked Installed, soonest install date first. Work it top to bottom.
Days out: negative = the install date has already passed · 0 = today · "needs date" = no install date set yet (these sort to the bottom and need scheduling).
Row colors in the queue: RED = late or installing today · AMBER = installing this week, or no date yet · GREEN = further out.
An account leaves the queue the moment its Equipment Status is set to Installed.
Deals that arrive in the AUTO section come in with a blank Equipment Status, so they show as "needs date" until the service team sets a status and an install date. That is the hand-off point from sales to service.
WHY THE CLOCK IS ON ITS OWN TAB
Only 4 rows are frozen at the top of the Installs tab (title, counters, column headers) so the account list scrolls normally. The detailed at-risk and prep lists live on the Install Clock tab, one click away via the link in cell C1.
NO DUPLICATES BETWEEN SALES AND SERVICE
The AUTO section only shows completed deals whose Customer Name is NOT already somewhere in the tracker above it.
The bottom of the Install Clock tab shows the reconciliation: how many deals are complete, how many are new to service, and how many were already being tracked.
Two account names were made consistent so the check matches: "Local Foods - ATX 2" → "Local Foods - ATX #2", and "Taha" → "Taha Market Mediterranean Foods".
If you ever want a completed deal to stop showing in the AUTO section, add it to the tracker above under the same name (or set its Equipment Status to Installed).

## Dashboard
SALES & LEASE DASHBOARD
Auto-updates from the Projected Sales or Lease tab. Deals marked X (fell through) are excluded from all figures except the "Fell Through" count.
Go to: | SOP | Projected Sales or Lease | Installs | Lists
Active Deals | Active Pipeline $ | Completed Deals | Completed $ | Total Booked $ (Active + Completed) | Fell Through
14 | 286643.36 | 15 | 453859.92 | 740503.28 | 0
BY PRODUCER — projected sales & leases
Producer | # Deals | Sales $ | Lease $ | Total $ | Completed # | Completed $ | Open $
Bill | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lance | 1 | 23953.08 | 0 | 23953.08 | 1 | 23953.08 | 0
Sean | 3 | 0 | 59728.4 | 59728.4 | 1 | 19800 | 39928.4
Shannon | 1 | 16051 | 0 | 16051 | 0 | 0 | 16051
Lizbeth | 10 | 238090.64 | 39600 | 277690.64 | 4 | 133008.38 | 144682.26
Amanda | 12 | 348080.16 | 15000 | 363080.16 | 9 | 277098.46 | 85981.7
Jesus | 0 | 0 | 0 | 0 | 0 | 0 | 0
(No producer / not on list) | 2 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 29 | 626174.88 | 114328.4 | 740503.28 | 15 | 453859.92 | 286643.36
BY PAYMENT TERMS |  |  |  | DEAL PROGRESS (active + completed)
Payment Terms | # Deals | Amount $ |  | Stage | # Deals | Amount $
Payment Plan | 2 | 118616.06 |  | Good to Order ✔ | 22 | 614521.86
50% Down + 50% upon install/30 days after | 4 | 73322.28 |  | Equipment Ordered ✔ | 21 | 594721.86
Lease | 6 | 114328.4 |  | Deal Complete ✔ | 15 | 453859.92
Paid in Full | 11 | 318255.12
(Not set) | 6 | 115981.42

## Projected Sales or Lease
PROJECTED SALES OR LEASE |  |  |  | Sales team: one row per deal — see the SOP tab for full instructions. Account Type flags Avi/Richard accounts. Deal Completion: ✔ = finalized (row turns green + deal auto-copies to the Installs tab) · X = fell through (row turns red, excluded from Dashboard).
Customer Name | Producer | Account Type | Date of Deal | Equipment | Equipment Deal Amount ($) | Good to Order ✔ | Equipment Ordered ✔ | Equipment ETA | Payment Terms | Invoice # | Deal Completion | Notes | new? | rank
Truffle & Rye | Amanda |  |  | La Marz GS3, jay grinder | 11118.85 | ✔ | ✔ | Here | Paid in Full | 740831 | ✔ | Waiting on broker to ship to Turks for final amount | 1 | 1
Jonathan's The Rub - Bridgeland | Amanda | Avi Account |  | Cameo c'2s | 22151.26 | ✔ | ✔ | Installed | Payment Plan | 734302 | ✔ |  | 1 | 2
Coco Crepe Elyson Town Center | Lizbeth |  |  | Eversys Enigma e'4s Classic | 37611.26 | ✔ | ✔ |  | Paid in Full | 745528 |  | Still under remodel | 0
Valentinas Coffee | Lizbeth |  |  | La Marzocco Strada XT 2 Group, Mazzer ZM Filter Grinder - Black, Mazzer Robur S Electronic, Puqpress Q2 Automatic Tamper BLACK, Everpure EZ-RO 200/10 Gallon Hydropneumatic Tank, Blendtec Stealth 885, Blendtec Rapid Rinse Station | 49601.19 | ✔ | ✔ |  | Paid in Full | 754770 754497 749838 | ✔ | Special order. Waiting on ETA from LM. | 1 | 3
El toro tex mex | Lizbeth | Avi Account |  | Eversys e'4 | 35000 | [6 empty] | Working on getting out of Coca Cola Lease | 0
Ciao Bella Bakery | [12 empty] | 0
Work Around Café | Amanda |  |  | strada s 2 gr, jay, mahl ek43, mahl e65, fetco 1251, itbdd, puq | 49930.42 | [7 empty] | 0
Coco Crepe Bellaire | Lizbeth |  |  | La Marzocco Linea Classic S 2 Group AV & La Marzocco Swift Dual-Hopper Espresso Grinder | 27271 | ✔ | ✔ | Here | 50% Down + 50% upon install/30 days after | 746261 |  |  | 0
Local Foods - ATX #2 | Amanda |  |  | La Marzocco Linea Classic S 2 Group AV & La Marzocco Swift Dual-Hopper Espresso Grinder, Fetco 1251, ITB-DD EZRO200 | 31902 | ✔ | ✔ | Here | Paid in Full | 746493 | ✔ |  | 0
Bella Flori | [12 empty] | 0
Luzia Coffee Shop | Lizbeth |  |  | Invicta 3GR, Robur S E, Puqpress | 26089.52 | ✔ | ✔ | Installed | Paid in Full | 748258 | ✔ | Pending Down Payment | 0
The Audrey Restaurant & Bar Post Oak | Lizbeth |  |  | Eversys Cameo c'2s | 19800 | ✔ | ✔ | Installed | Lease |  | ✔ |  | 1 | 4
Lakewood Yacht Club | Lizbeth | Avi Account |  | Eversys Cameo c'2s | 19800 | ✔ |  |  | Lease |  |  |  | 0
Common Bond Spring | Amanda | Avi Account |  | 2 x e4s with 1.5 wands SN: 0110710025266E0006 Fetco 1252 Plus SN: 1252UB23015260303 Bunn ITB-DD SN: ITB0065171 Fetco GRS1202 SN:12021A00020259710 | 96464.8 | ✔ | ✔ | Installed | Payment Plan | 749148 | ✔ |  | 0
CoPlay Cove | Lizbeth |  |  | e4s SN: 0110700025150E0012 | 37517.67 | ✔ | ✔ | Installed | Paid in Full | 735103 | ✔ |  | 0
Sunrise Coffee | Amanda |  |  | Linea S 2 Group SN:LS029320 Mazzer Super Jolly SN:2540764 | 21043.39 | ✔ | ✔ | Installed | Paid in Full | 751629 | ✔ |  | 0
Latte Cafe - La Grange | Amanda |  |  | Rancilio Classe 9 | 14018.16 | ✔ | ✔ | Installed | Paid in Full | 752128 | ✔ |  | 0
Taha Market Mediterranean Foods | Sean |  |  | Eversys Cameo c'2s | 19800 | ✔ | ✔ | Installed | Lease | X | ✔ |  | 0
Clover | Amanda |  |  | Eversys e'4s | 35400 | ✔ | ✔ | Installed | Paid in Full | 754732 | ✔ |  | 0
Parkwood American Grille | Amanda | Avi Account |  | Eversys Legacy | 16051.28 | ✔ | ✔ | Mid-August | 50% Down + 50% upon install/30 days after | 756106 |  | Will need Cameo until Legacycomes in. | 0
Uchi - Houston | Shannon |  |  | Eversys Legacy | 16051 | [6 empty] | Will use loaner Legacy unit trial is over | 0
Brews & Books | Lance |  |  | Eversys Cameo c'2s | 23953.08 | ✔ | ✔ | 2023-07-14 | Paid in Full | 755161 | ✔ |  | 1 | 5
Riot Comedy Club | Sean |  |  | Rancilio Classe 5 Compact, Mazzer SJ E, Mazzer Mini E | 11128.4 | ✔ | ✔ | Here | Lease |  |  | Tentative install date 7/28 earliest. | 0
Osso & Kristalla | Sean | Avi Account |  | Everysys E'4 | 28800 | ✔ | ✔ |  | Lease |  |  | Will be month to month, $800/mo | 0
bloom chica brew | Amanda |  |  | linea classic, jay grinder | 30000 | ✔ | ✔ |  | Paid in Full | 743957 | ✔ | 3rd party installation | 0
kol fac 118 | Amanda |  |  | cameo c'2s | 20000 | ✔ | ✔ |  | 50% Down + 50% upon install/30 days after | 756855 |  |  | 0
petroleum club | Amanda | Avi Account |  | cameo c'2s | 15000 | ✔ | ✔ | ready | Lease |  | ✔ |  | 0
Vam Foods #2 | Lizbeth |  |  | Bravilor Sego 12 120V | 10000 |  |  |  | 50% Down + 50% upon install/30 days after |  |  | Waiting for approval on purchase | 0
Mexico Lindo Bakery | Lizbeth |  |  | Rancilio Classe 5 USB 2 Group Auto-Volumetric | 15000 | [7 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Install Clock
⏱ INSTALL CLOCK
← Back to the Installation Tracker |  | Everything here is read-only and recalculates on open. Fix things on the Installs tab.
Today | This week (Mon–Sun) | Next week | ⚠ Equipment NOT ready | ⚠ Past due & not ready | ⚠ Customer not ready | Completed installs | In queue (not yet installed)
2026-08-20 | 8/17 – 8/23 | 8/24 – 8/30 | 0 | 0 | 0 | 41 | 13
⚠ AT RISK NOW — scheduled this week or next (or already past due) and not ready
# | Account | Why it's flagged | Equip Status | Install Date | Assigned Tech | Work Order | Requirements
✓ Nothing flagged — no scheduled account is at risk right now.
🔧 PREP QUEUE — every account not yet installed, in install-date order. Work top to bottom.
Days out | Account | Equipment to prep | Equip Status | Install Date | Assigned Tech | Work Order | Requirements
-7 | Ninfa's - Navigation | TB3 | Ready | 2026-08-13 |  |  |  | 33
0 | Southern Ice CO | bunn itcb | Ready | 2026-08-20 |  | WO-0406 | Ready | 52
needs date | kol fac 118 | cameo, itcb | Not Ready |  |  |  |  | 42
needs date | Coco Crepes Bellaire | La Marzocco Linea Classic S 2 Group AV/ La Marzocco Swift Dual-Hopper Espresso Grinder/ Bunn Axiom-APS | Not Ready |  |  |  |  | 45
needs date | waller county court house | axiom aps | Ready |  |  |  | Not Ready | 48
needs date | Doug's Diner | Fetco MBS x 2 / Powder Machine | Not Ready |  | 3rd Party |  | Ready | 50
needs date | Two Step Taqueria - South |  | Not Ready |  | Lance |  |  | 51
needs date | Scrambles Breakfast & Lunch | BUNN ITCB & BUNN G9 GRINDER | [5 empty] | 53
needs date | Truffle & Rye | La Marz GS3, jay grinder | [5 empty] | 161
needs date | Jonathan's The Rub - Bridgeland | Cameo c'2s | [5 empty] | 162
needs date | Valentinas Coffee | La Marzocco Strada XT 2 Group, Mazzer ZM Filter Grinder - Black, Mazzer Robur S Electronic, Puqpress Q2 Automatic Tamper BLACK, Everpure EZ-RO 200/10 Gallon Hydropneumatic Tank, Blendtec Stealth 885, Blendtec Rapid Rinse Station | [5 empty] | 163
needs date | The Audrey Restaurant & Bar Post Oak | Eversys Cameo c'2s | [5 empty] | 164
needs date | Brews & Books | Eversys Cameo c'2s | [5 empty] | 165
All 13 account(s) waiting to be installed are listed above.
Sales hand-off: 15 completed deal(s) on the Projected tab · 5 not yet in this tracker (shown in the AUTO section) · 10 already tracked, so not duplicated.

## Installs
INSTALLATION TRACKER |  | ⏱ Open the Install Clock →
Today | This week (Mon–Sun) | Next week | ⚠ Equipment NOT ready | ⚠ Past due & not ready | ⚠ Customer not ready | Completed installs | In queue (not yet installed) | Full detail — who is at risk and what to prep next — is on the Install Clock tab.
2026-08-20 | 8/17 – 8/23 | 8/24 – 8/30 | 0 | 0 | 0 | 41 | 13 | [7 empty] | 2026-08-17
Date Received | Customer Name | Equipment / Serial Numbers | Equipment Status | Install Date | Assigned Tech | Work Order | Requirements Ready? | Notes | Account Rep | Payment Status | Install Complete ✔ | ⚠ Install Alert |  |  | 2026-08-23
2026-05-13 | Wildwood | Fetco 52H SN:231515042 | Installed | 2026-05-27 | Josh | WO-9537 | Ready | Elia Bench 5/20/2026 | AL | No Purchased Equipment | ✔ |  |  | 999999999 | 2026-08-30 | 0
2026-04-29 | Gennaro's - Wimberly | Bunn ITCB | Installed | 2026-05-20 | Lance | WO-9469 | Ready |  | LO | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-04-29 | Common Bond Spring | 2 x e4s with 1.5 wands SN: 0110710025266E0006 Fetco 1252 Plus SN: 1252UB23015260303 Bunn ITB-DD SN: ITB0065171 Fetco GRS1202 SN:12021A00020259710 | Installed | 2026-05-28 | Josh | WO-9589 | Ready | All equipment needs to be benched Ryan Bench GR 1202 Elia Bench ITB-DD Josh Bench/setup 1x e4'ms 1.5 arm installed 05/28/2026 | AL | Payment Plan | ✔ |  |  | 999999999 |  | 0
2026-05-01 | Local Foods - ATX #2 | LM Linea S 2AV SN:LS028751 Swift Grinder SN:9386 Fetco 1251 SN:12511B23045259780 Bunn ITB-DD SN:ITB0065194 EZRO200-10 | Installed | 2026-07-21 | Oliver | WO-0134 | Ready | Linea, Swift, and fetco Benched by Oliver ITB-DD benched by Elias SWIFT is at Local Foods #1 Austin | AL/LO | Paid in Full | ✔ |  |  | 999999999 |  | 0
2026-05-01 | CoPlay Cove | e4s SN: 0110700025150E0012 Bunn Axiom-APS 120V SN: AXAP048647 | Installed | 2026-06-08 | Lance | WO-9698 | Ready | velvet / Decaf 8oz/12oz need kids temp steam (orig. install date entered as "Week of 6/8") | LR | Paid in Full | ✔ |  |  | 999999999 |  | 0
2026-05-01 | La Michoacana #52 - Dallas | Bunn ITCB 220V | Installed | 2026-06-02 | Bill | WO-9646 | Ready |  | LR | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-05-06 | Hunter Road Country Club | Bunn ITCB 120V SN:ITCB189507 | Installed | 2026-05-22 | Lance | WO-9470 | Ready | 85oz Airpots Ship on Wednesday truck. 5/20 Oliver Benched and Boxed for shipment 05/18 | AL/LO | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-05-18 | Cowgirl Coffee | Bunn Axiom-APS 120V SN:AXAP028340 | Installed | 2026-06-02 | Elias | WO-9477 | Ready | Elias benched 05/19 | AL/LO | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-05-22 | Sunrise Coffee | Linea S 2 Group SN:LS029320 Mazzer Super Jolly SN:2540764 | Installed | 2026-07-28 | Josh | WO-0143 | Ready | Need to pre-insepct first Velvet Esp 2oz | AL/LO | 50% Down / 50% at Install or Net 30 | ✔ |  |  | 999999999 |  | 0
2026-05-21 | Cherry Block | CWTF-APS Pour over | Installed | 2026-05-27 | Ryan | WO-9582 | Ready |  | LR | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-05-26 | Osso | Mazzer Mini Doser SN: 2318377 | Installed | 2026-06-02 | Ryan | WO-9600 | Ready | Adding Whole Bean espresso Elias Benching 6/1/2026 | SC | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-05-28 | Latte Cafe - La Grange | Classe 9 | Installed | 2026-06-04 | Oliver | WO-9598 | Ready | Ollie Calibrating josh verified working | JG | Paid in Full | ✔ |  |  | 999999999 |  | 0
2026-05-28 | Shirley's Donut | Bunn Axiom-APS 120V SN:AXAP049095 Bunn G9-2 Short SN: G900075916 | Installed | 2026-06-04 | Ryan | WO-9638 | Ready |  | LR | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-05-28 | Velocity Sim Lounge | Bunn Axiom SN:AXAP028345 | Installed | 2026-06-10 | Oliver | WO-9665 | Ready |  | AL | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-05-28 | Cheeks Coffee | ITCB SN: ITCB075996 | Installed | 2026-06-09 | Elias | WO-9672 | Ready |  | AL | Paid in Full | ✔ |  |  | 999999999 |  | 0
2026-06-04 | Kol Fac #113 | Bunn ITCB SN: ITCB082942 | Installed | 2026-06-10 | Oliver | WO-9697 | Ready |  | AL | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-06-09 | Audrey Post Oak | ITCB 220v SN:143215 Cameo - Not here yet. Need a loaner for Cameo | Installed | 2026-06-18 | Ryan | WO-9875 | Ready |  | LR | Lease | ✔ |  |  | 999999999 |  | 0
2026-06-11 | Sweet | Bunn Axiom-APS SN :AXAP049095 | Installed | 2026-06-15 | Oliver | WO-9642 | Ready | (orig. install date entered as "week of 6/15/2026") | AL/JG | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-06-11 | Taha Market Mediterranean Foods | Cameo - New in barn SN: 0099820025259C0040 | Installed | 2026-06-15 | Oliver | WO-9874 | Ready | (orig. install date entered as "week of 6/15/2026") | SM/RK | Lease | ✔ |  |  | 999999999 |  | 0
2026-06-16 | Tepatitlan Mexican Grill | Bunn ITCB 120v SN:ITCB064919 Bunn G9-2T SN:G900073972 | Installed | 2026-06-22 | Ryan | WO-9897 | Ready | Account is read. replacing same equipment. | LR | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-06-18 | Clutch Auto - Pearland | Bunn CWTF-APS (PO) SN:CWTF547359 | Installed | 2026-06-24 | Elias | WO-9941 | Ready | Pedro is gettting a unit ready | AL | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-06-18 | Clover | E4s | Installed | 2026-06-22 | Oliver | WO-9891 | Ready | getting e4s from lobby (orig. install date entered as "week of 6/22") | AL/JG | Paid in Full | ✔ |  |  | 999999999 |  | 0
2026-06-19 | Triple Steel - Galvestion | Bunn Axiom-APS | Installed | 2026-06-30 | Ryan | WO-9934 | Ready | (orig. install date entered as "week of 6/30") |  | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-06-29 | Helfman RiverOaks | Sego 12 SN:10140095 | Installed | 2026-07-14 | Elias | WO-0091 | Ready | Velvet Hot Choco Epouria milk | AL | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-06-30 | Uchi | Legacy | Installed | 2026-07-21 | Oliver | WO-0138 | Ready | Waiting on product and setting | SC |  | ✔ |  |  | 999999999 |  | 0
2026-06-30 | Parkwood American Grille | Legacy (Cameo loaner for the time being), ITCB | Installed | 2026-07-30 | Ryan | WO-0250 | Ready |  | AL | 50% Down / 50% at Install or Net 30 | ✔ |  |  | 999999999 |  | 0
2026-07-01 | Lakewoodd Yacht Club | 52H TB3 x 2 ITCB 220V L14-20 | Installed | 2026-07-22 | Ryan | WO-0151 | Ready |  | LR | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-07-06 | Rice University - South Main | ITCB 120V | Installed | 2026-07-09 | Elias | WO-0044 | Ready | Rice Settings | AL | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-07-07 | Ninfa's - Navigation | TB3 | Ready | 2026-08-13 |  |  |  | Additional Brewer | JG | No Purchased Equipment |  |  |  | 462470029 |  | 0
2026-07-10 | Luzia Coffee Shop | Invicta 3GR, Robur S E, Puqpress, Fetco51H, GR2.2, TB3 | Installed | 2026-07-27 | Josh | WO-0156 | Ready | 7/13 - preinspection | LR | 50% Down / 50% at Install or Net 30 | ✔ |  |  | 999999999 |  | 0
2026-07-10 | Coco Shrimp - Dallas | TB3 | Installed | 2026-07-13 | Bill | WO-0119 | Ready | Ship next week to Bill (orig. install date entered as "Week of 7/13/2026") | BM | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-07-14 | Brew & Books | Cameo c'2s | Installed |  | Lance | WO-0112 | Ready | Lance needs asap. JM & Decaf Esp | LO | 50% Down / 50% at Install or Net 30 | ✔ |  |  | 999999999 |  | 0
2026-07-15 | Rice University - Moody Center | Fetco 52H SN: F52H03082026 | Installed | 2026-08-04 | Elias | WO-0283 | Ready | New catering area | AL | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-07-15 | The Riot Comedy Club | Rancilio Classe 5 Compact SN:10467673, Mazzer SJ E SN:2601514, Mazzer Mini E SN:2608789 | Installed | 2026-08-13 | Charles | WO-0351 | Ready | (orig. install date entered as "Week of 7/27") | SM | Lease | ✔ |  |  | 999999999 |  | 0
2026-07-15 | La Lucha / Star Rover | Bunn ICB Tall | Installed | 2026-07-21 | Ryan | WO-9221 | Ready |  | SM | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-07-15 | Southerleigh SA Airport | Bunn ITCB | Installed | 2026-07-17 | Lance | WO-0125 | Ready |  | LO | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-07-23 | petroleum club | used cameo 2 step, itcb, g9-2t, fetco, gr2.2, TB3 | Installed | 2026-07-30 | Josh | WO-0251 | Ready | Fetcos Banquet: 1.5 gal and carafe Bunn Kitchen: 1 gallon and carafe. Coffee: Bayou and MB decaf | al | lease | ✔ |  |  | 999999999 |  | 0
2026-07-22 | kol fac 118 | cameo, itcb | Not Ready | [5 empty] | al | 50% Down / 50% at Install or Net 30 |  |  |  | 999900038 |  | 0
2026-07-22 | bloom chica brew | la marz linea, jay grinder | Installed | 2026-08-06 | 3rd Party | WO-0267 | Ready | Reached out Coffee Maverick | AL | Paid in Full | ✔ |  |  | 999999999 |  | 0
2026-07-21 | HEB Division Office | Bunn Axiom-TC Bunn LPG | Installed | 2026-07-30 | Bill | WO-0262 | Ready |  | BM | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-07-23 | Coco Crepes Bellaire | La Marzocco Linea Classic S 2 Group AV/ La Marzocco Swift Dual-Hopper Espresso Grinder/ Bunn Axiom-APS | Not Ready | [5 empty] | LR | Paid in Full |  |  |  | 999900041 |  | 0
2026-07-23 | Vam Foods | Bravilor Sego 12 120V & QTY 2 Airpot Brewers | Installed | 2026-08-06 | Ryan | WO-0312 | Ready |  | LR | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-07-31 | Sage The Vilage School | e4 & itcb from cafeteria to new coffee shop | Installed | 2026-08-06 | Oliver | WO-0181 | Ready | they own the e4 and loan the ictb | al | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-08-03 | waller county court house | axiom aps | Ready |  |  |  | Not Ready |  | al | No Purchased Equipment |  |  |  | 999900044 |  | 0
2026-08-04 | Hawker's Franklin | Bunn ITCB | Installed | 2026-08-23 | 3rd Party | WO-0314 | Ready |  | SC | No Purchased Equipment | ✔ |  |  | 999999999 |  | 0
2026-08-04 | Doug's Diner | Fetco MBS x 2 / Powder Machine | Not Ready |  | 3rd Party |  | Ready |  | SC | No Purchased Equipment |  |  |  | 999900046 |  | 0
2026-08-12 | Two Step Taqueria - South |  | Not Ready |  | Lance |  |  | They need a 51h to replace an ITCB |  | No Purchased Equipment |  |  |  | 999900047 |  | 0
2026-08-13 | Southern Ice CO | bunn itcb | Ready | 2026-08-20 |  | WO-0406 | Ready | waiting on paperwork, need to send a loaner | al | No Purchased Equipment |  |  |  | 462540048 |  | 0
2026-08-17 | Scrambles Breakfast & Lunch | BUNN ITCB & BUNN G9 GRINDER | [11 empty] | 999900049 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
AUTO — NEW COMPLETED DEALS (from Projected Sales or Lease). Only deals whose Customer Name is NOT already in the tracker above appear here, so nothing is duplicated. Green cells update themselves — do not type in them. Fill in Status, Install Date, Assigned Tech, Work Order, Requirements Ready?, and Notes as usual.
| Truffle & Rye | La Marz GS3, jay grinder | [6 empty] | AL | Paid in Full |  |  | 3 | 999900157 |  | 0
| Jonathan's The Rub - Bridgeland | Cameo c'2s | [6 empty] | AL | Payment Plan |  |  | 4 | 999900158 |  | 0
| Valentinas Coffee | La Marzocco Strada XT 2 Group, Mazzer ZM Filter Grinder - Black, Mazzer Robur S Electronic, Puqpress Q2 Automatic Tamper BLACK, Everpure EZ-RO 200/10 Gallon Hydropneumatic Tank, Blendtec Stealth 885, Blendtec Rapid Rinse Station | [6 empty] | LR | Paid in Full |  |  | 6 | 999900159 |  | 0
| The Audrey Restaurant & Bar Post Oak | Eversys Cameo c'2s | [6 empty] | LR | Lease |  |  | 14 | 999900160 |  | 0
| Brews & Books | Eversys Cameo c'2s | [6 empty] | LO | Paid in Full |  |  | 24 | 999900161 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0
[14 empty] | 999999999 |  | 0

## Lists (hidden)
Technicians | Call Status | Call Type | Yes/No | Equip Status | PM Style | Parts Status | PM Status | Account Reps | Checkbox helper | Add new technicians, statuses, or reps to these lists and the dropdowns on every tab update automatically. | Module Platform | Module Type | Module Status | Internal Techs | Payment Status | Producers | Payment Terms | Completion | Account Type | Producer (map) | Initials | Requirements Ready?
Josh | Open | Field Service | Y | Ready | 6 month PM | Yes - All Available | Pending Scheduling | AL | ✔ |  | Cameo | Brew Module | Not Started | Ryan | 50% Down / 50% at Install or Net 30 | Bill | Payment Plan | ✔ | Avi Account | Bill | BM | Ready
Oliver | Phone Resolved | In-House Rebuild | N | Not Ready | 12 month PM | Partial | Scheduled | LO |  |  | Enigma / e'Line | Medium Brew Module | In Progress | Elias | Paid in Full | Lance | 50% Down + 50% upon install/30 days after | X | Richard Account | Lance | LO | Not Ready
Charles | Dispatched | Installation |  | Installed | 36 month PM | No - Awaiting Parts | Awaiting Parts | LR |  |  | Legacy | Large Brew Module | Waiting on Parts | Oliver | Lease | Sean | Lease |  |  | Sean | SM
Elias | In Progress |  |  |  | Grinder PM | On Order | Ready to Dispatch | JG |  |  |  | Steam S Module | Ready | Josh | No Purchased Equipment | Shannon | Paid in Full |  |  | Shannon | SC
Ryan | Completed |  |  |  |  | TBD / Check Inventory | In Progress | SC |  |  |  | Steam M Module | Ship to Eversys (Core Swap) | Charles | Payment Plan | Lizbeth |  |  |  | Lizbeth | LR
Bill | Follow-up Needed | [5 empty] | Completed | SM |  |  |  | Hydraulic Module | At Eversys - Awaiting Return | Bill |  | Amanda |  |  |  | Amanda | AL
Lance | Cancelled | [5 empty] | Cancelled | RK |  |  |  | Grinder Module | Installed at Account | Lance |  | Jesus |  |  |  | Jesus | JG
3rd Party | [7 empty] | BM |  |  |  | Milk Module | Retired / Scrapped
Pump Module
Powder Module